## Slide 1: Executive Sponsors Meeting
March 22, 2018

## Slide 2: Agenda
Status Dashboard
Support Approach (Draft)
Project Schedule
Testing Entry / Exit Criteria
Revised Information Flow
Special Requests
Customization / Interface Update
Risks and Mitigation
Action Items – Previous Meeting

## Slide 3: Status Dashboard
Topic | Milestone | Status Towards Milestone | Comments
Design / Test | Scripting ready 3/12 |  | Testing and UAT preparations continue, with support from consultants
Conversion | All tickets resolved by 4/13 for next conversion cycle |  | Managing scope for a targeted 85% accurate conversion run in April / May 2018 Continue to focus on working issues / closing tickets
Interfaces | Interfaces tested by Rice and ready for UAT by 3/12 |  | Blackbaud resource onsite 3/5 for testing support Interfaces being tested and prioritized for go-live
Reporting | Reporting design complete 3/9 |  | After Blackbaud onsite, revised functional design delivered (under review)
Scope | N/A |  | Additional change orders continue to be identified Changes are being prioritized for go-live criticality
Budget | N/A |  | Expenditures appear to be in line with approved funding
Technical | 2/23 |  | Load balancer upgrade completed on time
Deployment Readiness | UAT 1 checkpoint by 4/13 |  | Precision Partners survey – responses being compiled Checkpoint after first round of testing
Y
Y
R
OwlConnect Project Overall Status
Y
Y
C
Y
Y
G

## Slide 4: Project Schedule
Go-live is scheduled for July 2018, following fiscal year-end close.
The project has entered the testing phase.
Go / No-Go: week of June 11

## Slide 5: Test Entry / Exit Criteria
ENTRANCE CRITERIA | Status
Configuration/setups completed | Y
Test instance created | G
Interfaces ready for testing | Y
Test condition Scripting >90% complete | Y
Functional and technical teams on standby for break-fix work | Y
Required test data documented and set up for testing | G
EXIT CRITERIA | Target | Actual | OK?
Successful execution of ‘required’ test conditions | >90% |  | 
Test results documented for executed scripts | 100% |  | 
Overall script execution | >90% |  | 
Open ‘Critical’ issues/work requests | <10 / <10% |  | 
Testers participation according to schedule | >90% |  | 
Acceptance of risk associated with outstanding issues | Yes |  | 

## Slide 6: Revised Information Flow: Design Status
Corporate Participation in Job Fairs, Events, and Recruiting
Linked Documents
Financial
BB CRM
Gifts
Financial Aid
Payroll
Scholarships
Campus Call
Students / Faculty, Staff
Sallyportal
BBIS
Web Forms
OnBase - AE
Rice DW
Pres Partner Dashboard
Handshake
Gifts / Bio Updates
Alumni, Faculty, Parents
Payroll Deductions
Master Data
Funds
Key
One way: to CRM
One way: from CRM
Two way
Banner
Sponsored Research
Bio Updates
Sponsored Research
Current SQL Database
BB DW
Key:
Being Tested
Issues Found
Not yet designed

## Slide 7: Special Requests
Request | Cost | Status
Data Warehouse Extension | One time, $15k | Open request
Possible plug-in for 2 factor authentication | $20K | Open request
Reporting design onsite closeout (2 onsite) | 40 hours no cost to Rice | Approved
Bing maps | $ 120 / year for 3 years | Open request
Custom Name Formats | $ 5,000 one time + 30 hours | Approved
Data Loader (Precision Partners) | $ 15,000 / year for 3 years | Approved
Extra conversion support from PP | $ 21,000 | Approved
Engagement of Zuri Group consultants | $ 80,000 | Approved
Additional Blackbaud support for go-live (515 hrs), including: Secure access to alumni resources (50 hrs) Custom Name Formats modification (30 hrs) | $ 80,975 | Approved
Secure access to alumni resources | 50 hours (estimated 10,000) | Approved

## Slide 8: Risks and Mitigation
# | Risk / Issue | Mitigation | Change
1 | Time required from DAR employees continues to escalate: UAT, preparations for next conversion cycle, planning for post go-live support model. | Support by Zuri (UAT) and Precision Partners (Conversion); requirements for support model under development with leads | 
2 | Data conversion: New scope adding risk to next conversion cycle | Blackbaud conversion analyst to estimate impact of new requirements; change requests will be evaluated for priority and timing | 
3 | Jones School resource availability limited to focus on OwlConnect | Resource availability to perform cleanup, project activities, and future support remains a risk. Karen has begun conversations with Jody Sommer and Katherine Schieffelin | 
4 | Readiness for UAT | Engaged Zuri group for scripting support; developed highest priority scripts for first week of UAT | 
5 | Budget risk - Additional functionality requested from Blackbaud to fit business requirements | Budget reviewed and so far within allocated funding | 
6 | June / July business processes may be impacted by Go Live and Stabilization requirements | Discussions upcoming: expectations and activities during / after go-live | 
7 | Reporting delayed | Reporting design delivered, under review | 
R
Y
R
G
Y
Y
Y
Notes: Back pocket: Slippage and impact..

## Slide 9: Action Items – Previous Meeting
Action | Responsible | Status
Executive Sponsor Review call with Blackbaud | Karen | Held on March 20
Follow up – future support plans for Jones and Baker Institute | Darrow / Karen | Jones support discussions taking place
Schedule OwlConnect presentation at Deans’ Council | Darrow / Klara | Schedule for February
Schedule Glasscock presentation / WIIFM | Kathy / Karen | For discussion with Dauwn
Implementation of 2-factor authentication | Kathy / Karen | Upcoming meeting on Thursday to review Blackbaud proposal for plug-in
Begin planning for support | Karen | Included for discussion / BAC topic